APP DEV HORIZON  ·  FALL 2026

Roadmap

Sorted by return. Hours assume familiarity with this codebase. Capacity at 8 part-time devs × 5 hrs/week × 14 weeks = 560 hrs.

Phase 0 — Deploy to App Dev's AWS  ·  55 hrs  ·  5 people  ·  wks 1–3

| Item | Sub-task | Hours |
| --- | --- | --- |
| AWS deploy | Own account in nonprod OU | 25 |
|  | RDS Postgres replaces SQLite + in-memory staging |  |
|  | Fargate / App Runner |  |
|  | Secrets Manager replaces .env |  |
|  | EventBridge runs nightly + weekly |  |
| Reconnect Authentik | Restore OIDC validation (auth.py returns hardcoded admin today) | 15 |
|  | admin / portfolio_leader / project_lead mapping |  |
|  | Gates items 1, 2, 4 |  |
| Spend cap + run health | Per-run token budget, hard stop | 10 |
|  | Backoff on model failures |  |
|  | Panel: last run cost, duration, success |  |
| People Portal | Now required, not optional — item 2 depends on it | 5 |
|  | URL has no scheme and no token; fails every run |  |
|  | Reports partial instead of not configured |  |

Features by ROI  ·  345 hrs

| # | Feature | Sub-task | Hours | People | Cal. |
| --- | --- | --- | --- | --- | --- |
| 1 | SOW → weekly tasks | Upload + PDF/DOCX parse, versioned store, confidential access (15) | 70 | 3 devs + design | 4 wks |
|  |  | LLM decomposes deliverables → week-by-week plan; mandatory lead edit (25) |  |  |  |
|  |  | Assign to engineers, per-member task list, status (20) |  |  |  |
|  |  | Link tasks to commits/PRs for auto-progress (10) |  |  |  |
|  |  | Reuses /spec/decompose + ci_agent.py, both currently dead |  |  |  |
| 2 | Project setup from People Portal | Fix the adapter (Phase 0) and turn the catalog fold on | 10 | 1 dev | 2 wks |
|  |  | Projects + boundaries created from the Portal record — leads register there, not in Horizon |  |  |  |
|  |  | Reconcile Portal project ↔ Gitea org, flag mismatches for admin review |  |  |  |
|  |  | Drop discover-projects and the admin token path |  |  |  |
|  |  | fold_people_portal_catalog already writes both documents; dead only because the adapter is misconfigured |  |  |  |
| 3 | Weekly digest — Slack + email | Slack per-project thread for tech leads | 25 | 2 devs | 3 wks |
|  |  | Monday portfolio email for exec board |  |  |  |
|  |  | One payload, two renderers, deep links |  |  |  |
|  |  | Templating, unsubscribe, delivery failures |  |  |  |
| 4 | Contribution & Growth | Identity resolution: Gitea login → member, reviewable map, manual override (15) | 50 | 2 devs + design | 4 wks |
|  |  | Data model: member × week × project, backfills from archive (5) |  |  |  |
|  |  | My profile — full self-view, ship first (10) |  |  |  |
|  |  | Team roster: active weeks, tasks, review load, coverage; alphabetical (10) |  |  |  |
|  |  | Portfolio view, aggregate only, floor 5 (5) |  |  |  |
|  |  | Growth signals: breadth, reciprocity, trajectory (5) |  |  |  |
| 5 | Leaderboard / recognition | Rotating monthly categories: most reviews given, most repos helped on, biggest first-week jump, most PRs unblocked | 20 | 1 dev | 4 wks |
|  |  | Named winner per category, no full ordered list |  |  |  |
|  |  | Opt-out |  |  |  |
|  |  | Straight commit ranking instead = 10 hrs, opt-in, monthly reset |  |  |  |
| 6 | Org map | Tree: club → division → team → project → members | 35 | 1 dev + design | 4 wks |
|  |  | Live status per node (project signal, member tasks) |  |  |  |
|  |  | Click to drill in, read-only |  |  |  |
|  |  | Hierarchy pull already staged in ingestion.py, unread |  |  |  |
| 7 | Was Horizon right? | Record actual outcome per project at semester end | 20 | 1 dev | 4 wks |
|  |  | Compare to wk 4 / 8 / 12 calls |  |  |  |
|  |  | Publish hit rate incl. misses |  |  |  |
| 8 | Semester one-pager | Portfolio at a date, printable | 15 | 1 dev | 3 wks |
|  |  | Per project: trajectory, shipped, open |  |  |  |
|  |  | No new data, straight from snapshots |  |  |  |
| 9 | Evidence beyond code | Accept design files, docs, written updates | 50 | 3 devs | 4 wks |
|  |  | Extend evidence reader + signal prompt |  |  |  |
|  |  | Fairness: designers/PMs currently read as dead projects |  |  |  |
| 10 | Where work is stuck | PRs aging without a reviewer | 30 | 2 devs | 3 wks |
|  |  | Review load on one person |  |  |  |
|  |  | Branches that never merge |  |  |  |
|  |  | Data already in activity rows |  |  |  |
| 11 | Public impact page | Curated aggregate view of the semester | 20 | 1 dev + design | 2 wks |
|  |  | No individual data, no risk signals |  |  |  |
|  |  | Recruiting / sponsorship value |  |  |  |

Phasing

| Phase | Items | Hours | People |
| --- | --- | --- | --- |
| 0 · Platform | AWS, Authentik, spend cap, People Portal | 55 | 5 |
| 1 · Tech leads | 1, 2, 3 | 105 | 7 |
| 2 · Members | 4, 5, 6 | 105 | 6 |
| 3 · Breadth | 7, 8, 9, 10, 11 | 135 | 8 |
| Total | 11 features + platform | 400 | 8 peak |

400 of 560 hrs capacity — 160 hrs (29%) held back for exams, onboarding and attrition. Phase 0 wks 1–3, Phase 1 wks 3–6, Phase 2 wks 7–10, Phase 3 wks 11–14.